## Sheet1
Center for Spiritual Living Greater Dayton
Extreme Makeover project list
AREA |  |  | Priority | Skilled work | Additional Costs Not budgeted | Materials Needed
| Stage | [5 empty] | Priority
|  | Window cover | 1 | FIT |  |  | 1 - ASAP
|  | Hang art work | 1 |  |  |  | 2 - end of year
|  | Organize and declutter equipment | 1 | Kenny/Band |  |  | 3 - next spring
|  | Hang speakers? | 1 | FIT
|  | Carpeting | 1 | contracted
|  | Touchup all paint as needed | 1
Sanctuary
|  | Carpeting | 1 | contracted
|  | Paint all trim and baseboard | 1
|  | Touchup all paint as needed | 1
|  | Blinds/curtains for side/back windows | 1 | FIT
|  | Ceiling repairs | 1 | FIT
|  | Build mini-stage? | 1 | FIT
|  | Replace electrical outlets and cover plates | 1
|  | Build literature shelf near Welcome Center | 1 | FIT
|  | Side wall light sconces | 2 | FIT
Entryway
|  | Floor tile | 2 | contracted
|  | Table/furniture | 2
|  | Paint door | 1
|  | Window - posters relocated to weather-proof door mounted case outside? | 1 | FIT
|  | Paint register | 1
New Bookstore
|  | Finish paint | 1
|  | Cash register closet shelf | 1 | FIT
|  | Lockset for door | 1 | FIT
|  | Signage | 1
Library
|  | Repair back wall under window | 3
|  | Replace table | 3
|  | Paint including doors | 3
|  | New whiteboard | 3
|  | Lighting | 3
|  | Rug - clean or replace | 3
Social Hall
|  | Clean floors | 1 | contracted
|  | Declutter | 1
|  | Artwork | 2
|  | New tables | 3
Hallway
|  | Carpeting |  | contracted
|  | Paint all trim and baseboard | 1
|  | Discard literature shelf | 2
|  | Hang bulletin boards | 2 | FIT
|  | Paint doors | 2
Restrooms
|  | Paint | 1
|  | Flooring? | 2 | contracted
|  | Light fixtures | 2 | FIT
|  | Signage | 1
|  | Artwork? | 3
|  | Paint doors | 1
Hallway to community room
|  | Remove bulletin boards | 3
|  | Repair wall | 3
|  | Paint wall | 3
|  | Reinstall bulletin boards | 3
|  | Room signage | 3
Back bathroom
|  | Refurbish | 3
Children's room
|  | Finish painting | 1
|  | New door | 2 | FIT
|  | Artwork | 2
|  | Carpeting | 1 | contracted
Toddlers room
|  | Carpeting | 1 | contracted
Community room
|  | Carpeting | 1 | contracted
Kitchen
|  | Paint | 3
|  | Flooring | 3 | contracted
Rev CC Office
Remove wallpaper/repair wall
Painting
Lighting
Center Office
Remove wallpaper/repair wall
Painting
Reconfigure furniture
Organize wiring
New Conference room (old bookstore)
|  | Door locksets | 1